## Slide 1: Plan for 3D Deep
Jungwon Kang, Maryam Jameela, Razieh Ramak
Sept 30 2018
Ver 1

## Slide 2: Objectives
Building 1st Version Deep Network for Each Task
Task | Major Contributor | Objectives
Noise filtering (for Optech) | Razieh Ramak | Point cloud segmentation (Noise/Non-noise), non real-time
Point cloud segmentation (for Optech) | Maryam Jameela | Point cloud segmentation (N-class objects), non real-time
3D object detection (for Thales) | Jungwon Kang | Real-time 3D object detection

## Slide 3: Schedule
Month | Task | Deliverable
Oct 2018 | • Problem definition • Dataset preparation • Literature survey | • Document describing problem definition, dataset, and literature survey • Visualization of dataset
Nov | • Practicing deep library • Design & implementation | • Document describing design
Dec | • Implementation | • Source code (Dec 31)
Jan 2019 | • Documentation | • Document describing implementation (Jan 15)
*Submission deadline of major conferences starts from March.

## Slide 4: Management Policy
Regular meeting or discussion biweekly
Team website:
  https://github.com/yorku-ausml/deep3d

## Slide 5: To-do List
Problem definition, including
  Cause of noise (Razieh)
  Object classes (Maryam, Jungwon)
Dataset description, including
  Existing Optech airborne dataset (Razieh)
  Dataset size
  Current repository
  Visualization
Etc
  Finding point cloud label tool (for making ground-truth)
  Finding visualization tool
Written on Oct 1 2018

## Slide 6: Key Literature
Point cloud segmentation
  Large-scale point cloud segmentation with superpoint graphs https://github.com/loicland/superpoint_graph *Rank 1 in http://www.semantic3d.net/
  PointNet++: deep hierarchical feature learning on point sets in a metric space https://github.com/charlesq34/pointnet2 *Rank 4 in http://www.semantic3d.net/
Object detection
  Joint 3D proposal generation and object detection from view aggregation https://github.com/kujason/avod
Written on Oct 1 2018
*Literature list is also available at https://github.com/yorku-ausml/deep3d/wiki/Related-works

## Slide 7: Current Progress
Oct 12 2018

## Slide 8: Asana Assignment
A

## Slide 9: Key Papers
Point cloud segmentation
  PointNet: Deep Learning on Point Sets for 3D Classification and Segmentation https://github.com/charlesq34/pointnet *Both used in the two following papers
  PointNet++: deep hierarchical feature learning on point sets in a metric space https://github.com/charlesq34/pointnet2 *Rank 4 in http://www.semantic3d.net/
  Large-scale point cloud segmentation with superpoint graphs https://github.com/loicland/superpoint_graph *Rank 1 in http://www.semantic3d.net/

## Slide 10: Publicly Available Dataset (1/3)
Semantic3D
  LiDAR dataset with over 3 billion points from a variety of urban and rural scenes.
  http://www.semantic3d.net/
  Managed by ETH (http://www.prs.igp.ethz.ch/)
  8 class labels, namely {1: man-made terrain, 2: natural terrain, 3: high vegetation, 4: low vegetation, 5: buildings, 6: hard scape, 7: scanning artefacts, 8: cars}.

## Slide 11: Publicly Available Dataset (2/3)
S3DIS (Stanford Large-Scale 3D Indoor Space)
  3D RGB point clouds of six floors from three different buildings
  http://buildingparser.stanford.edu/dataset.html
  Currently, 2D-3D-S dataset is newly released.
  13 object classes (ceiling, floor, wall, beam, column, window, door, and movable elements: table, chair, sofa, bookcase, board and clutter for all other elements)

## Slide 12: Publicly Available Dataset (2/3)
Etc
  Oakland 3-D Point Cloud Dataset (2009)
    http://www.cs.cmu.edu/~vmr/datasets/oakland_3d/cvpr09/doc/
  NYU Depth Dataset V2 (2012)
    https://cs.nyu.edu/~silberman/datasets/nyu_depth_v2.html
  Sydney Urban Objects data set
    http://www.acfr.usyd.edu.au/papers/SydneyUrbanObjectsDataset.shtml
  IQmulus & TerraMobilita Contest
    Mobile laser scans (MLS) in dense urban environments
    http://data.ign.fr/benchmarks/UrbanAnalysis/
  Vaihingen3D airborne benchmark
    http://www2.isprs.org/commissions/comm3/wg4/3d-semantic-labeling.html

## Slide 13: PointNet
Architecture
  http://stanford.edu/~rqi/pointnet/
CVPR 2017

## Slide 14: PointNet++
Hierarchical Feature Learning Architecture
  http://stanford.edu/~rqi/pointnet2/
NIPS 2017

## Slide 15: Superpoint Graph (1/2)
Individual steps in pipeline
CVPR 2018

## Slide 16: Superpoint Graph (2/2)
CVPR 2018

## Slide 17: Plan
aaa